## Defects
Defect # | Status | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity
1 | Closed | Tom Rick | v2 | NC4 | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown In Name Field | An error message "Numbers are not allowed" is shown | Medium | Medium
2 | Closed | Tom Rick | v2 | NC5 | "1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field" | An error message "ADDRESS cannot be empty" must be shown in Address Field | No error message is shown | Medium | Medium
3 | Closed | Tom Rick | v2 | NC6 | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in Address Field | No error message is shown | Medium | Medium
4 | Closed | Tom Rick | v2 | NC11 | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in City Field | An error message "Numbers are not allowed" is shown | Medium | Medium
5 | Closed | Tom Rick | v2 | NC15 | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown | An error message "Numbers are not allowed" is shown | Medium | Medium
6 | Closed | Tom Rick | v2 | NC20 | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown | An error message "Characters are not allowed" is shown | Medium | Medium
7 | Closed | Tom Rick | v2 | NC21 | 1) Enter First character Blank space | An error message "PIN cannot have space" must be shown | An error message "Characters are not allowed" is shown | Medium | Medium
9 | Closed | Tom Rick | v2 | NC24 | 1) Enter Blank space in Telephone | An error message "Telephone cannot have be space" must be shown | An error message "Characters are not allowed" is shown | Medium | Medium
8 | Closed | Tom Rick | v2 | NC23 | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown | An error message "Characters are not allowed" is shown | Medium | Medium
10 | Deffered | Tom Rick | v2 | NC29 | 1) Enter Blank space in Email | An error message "Email-ID is not valid" must be shown | No error message is shown | Low | Low
11 | Closed | Tom Rick | v2 | NC30 | Cross check Field names with that in SRS | Field names in SRS and system should match | telephone number will be "Mobile number" | Medium | Medium
12 | Closed | Tom Rick | v2 | EC4 | "1) Enter valid Customer id 2) Submit" | Edit Customer successfully redirect to Edit Customer Page | "Connection Error is shown "" Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/editCustomerPage.php on line 3 could not connect Access denied for user 'root'@'localhost' (using password: NO) """ | High | High
13 | Closed | Tom Rick | v2 | EC5 | "1) Do not enter a value in NAME Field 2) Press TAB and move to next Field" | An error message "Name cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
14 | Closed | Tom Rick | v2 | EC6 | 1) Enter numeric value in NAME Field | An error message "Name cannot contain numbers" must be shown | Cannot be executed due to connection issue | High | High
15 | Closed | Tom Rick | v2 | EC7 | 1) Enter Special Character In NAME Field | An error message "Name cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | High | High
16 | Closed | Tom Rick | v2 | EC8 | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | An error message "ADDRESS cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
17 | Closed | Tom Rick | v2 | EC9 | 1) Do not enter a value in CITY Field 2) Press TAB and move to next Field | An error message "CITY cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
18 | Closed | Tom Rick | v2 | EC10 | 1) Enter numeric value in CITY Field | An error message "City cannot contain Number" must be shown | Cannot be executed due to connection issue | High | High
19 | Closed | Tom Rick | v2 | EC11 | 1) Enter Special Character In CITY Field | An error message "City cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | High | High
20 | Closed | Tom Rick | v2 | EC12 | 1) Do not enter a value in STATE Field 2) Press TAB and move to next Field | An error message "STATE cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
21 | Closed | Tom Rick | v2 | EC13 | 1) Enter numeric value in STATE Field | An error message "Numbers are not allowed" must be shown | Cannot be executed due to connection issue | High | High
22 | Closed | Tom Rick | v2 | EC14 | 1) Enter Special Character In STATE Field | An error message "City cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | High | High
23 | Closed | Tom Rick | v2 | EC15 | 1) Enter character value in PIN Field | An error message "PIN cannot contain character" must be shown | Cannot be executed due to connection issue | High | High
24 | Closed | Tom Rick | v2 | EC16 | 1) Do not enter a value in PIN Field 2) Press TAB and move to next Field | An error message "PIN cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
25 | Closed | Tom Rick | v2 | EC17 | 1) Enter More than 6 digit in PIN field 2) Enter Less Than 6 digit in PIN field | An error message "PIN must contain 6 digit" | Cannot be executed due to connection issue | High | High
26 | Closed | Tom Rick | v2 | EC18 | 1) Enter Special Character In PIN Field | An error message "PIN cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | High | High
27 | Closed | Tom Rick | v2 | EC19 | 1) Do not enter a value in Telephone Field 2) Press TAB and move to next Field | An error message "Telephone cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
28 | Closed | Tom Rick | v2 | EC20 | 1) Enter Special Character In PIN Field | An error message "Telephone cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | High | High
29 | Closed | Tom Rick | v2 | EC21 | 1) Do not enter a value in Email Field 2) Press TAB and move to next Field | An error message "Email cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
30 | Closed | Tom Rick | v2 | EC22 | Enter invalid email in Email field | An error message "Email must be in format example@example.com" must be shown | Cannot be executed due to connection issue | High | High
31 | Closed | Tom Rick | v2 | EC23 | Enter invalid email in Email field | An error message "Email must be in format Example@example.com" must be shown | Cannot be executed due to connection issue | High | High
32 | Closed | Tom Rick | v2 | NA2 | 1) Enter character value in Customer id Field | An error message "Customer id must be numeric" must be shown | No error message is shown | Medium | Medium
33 | Closed | Tom Rick | v2 | NA3 | 1) Enter Special Character In Customer id Field | An error message "Customer id cannot have special character" must be shown | No error message is shown | Medium | Medium
34 | Closed | Tom Rick | v2 | NA4 | 1) Customer Id cannot have Blank space 2) Press Tab | An error message "Customer id cannot have blank space" must be shown | No error message is shown | Medium | Medium
35 | Closed | Tom Rick | v2 | NA5 | 1) Enter first character space 2) Press Tab | An error message "Customer id cannot have first character space" must be shown | No error message is shown | Medium | Medium
36 | Closed | Tom Rick | v2 | NA6 | 1) Do not enter a value in Initial Deposit Field 2) Press TAB and move to next Field | An error message "Initial deposit cannot be empty" must be shown | No error message is shown | Medium | Medium
37 | Closed | Tom Rick | v2 | NA7 | 1) Enter character value in Initial Deposit Field | An error message "Initial Deposit must be numeric" must be shown | No error message is shown | Medium | Medium
38 | Closed | Tom Rick | v2 | NA8 | 1) Enter Special Character In Initial Deposit Field | An error message "Initial Deposit cannot have special character" must be shown | No error message is shown | Medium | Medium
39 | Closed | Tom Rick | v2 | NA9 | 1) Initial Deposit cannot have Blank space 2) Press Tab | An error message "Initial Deposit cannot have blank space" must be shown | No error message is shown | Medium | Medium
40 | Closed | Tom Rick | v2 | NA10 | 1) Enter first character space 2) Press Tab | An error message "Initial Deposit cannot have first character space" must be shown | No error message is shown | Medium | Medium
41 | Closed | Nick Price | v2 | EA4 | 1) Enter valid Account Number 2) Submit | Edit Account successfully redirect to Edit Account Form | Connection Error is shown " Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/editCustomerPage.php on line 3 could not connect Access denied for user 'root'@'localhost' (using password: NO) " | High | High
42 | Closed | Nick Price | v2 | EA7 | 1) Do not enter a value in Customer id Field 2) Press TAB and move to next Field | An error message "Customer id cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
43 | Closed | Nick Price | v2 | EA8 | 1) Enter character value in Customer id Field | An error message "Customer id must be numeric" must be shown | Cannot be executed due to connection issue | High | High
44 | Closed | Nick Price | v2 | EA9 | 1) Enter Special Character In Customer id Field | An error message "Customer id cannot have special character" must be shown | Cannot be executed due to connection issue | High | High
45 | Closed | Nick Price | v2 | EA10 | 1) Customer Id cannot have Blank space 2) Press Tab | An error message "Customer id cannot have blank space" must be shown | Cannot be executed due to connection issue | High | High
46 | Closed | Nick Price | v2 | EA11 | 1) Enter first character space 2) Press Tab | An error message "Customer id cannot have first character space" must be shown | Cannot be executed due to connection issue | High | High
47 | Closed | Nick Price | v2 | EA12 | 1) Do not enter a value in Balance Field 2) Press TAB and move to next Field | An error message "Balance cannot be empty" must be shown | Cannot be executed due to connection issue | High | High
48 | Closed | Nick Price | v2 | EA13 | 1) Enter character value in Balance Field | An error message "Balance must be numeric" must be shown | Cannot be executed due to connection issue | High | High
49 | Closed | Nick Price | v2 | EA14 | 1) Enter Special Character In Balance Field | An error message "Balance cannot have special character" must be shown | Cannot be executed due to connection issue | High | High
50 | Closed | Nick Price | v2 | EA15 | 1) Balance cannot have Blank space 2) Press Tab | An error message "Balance cannot have blank space" must be shown | Cannot be executed due to connection issue | High | High
51 | Closed | Nick Price | v2 | EA16 | 1) Enter first character space 2) Press Tab | An error message "Balance cannot have first character space" must be shown | Cannot be executed due to connection issue | High | High
52 | Closed | Nick Price | v2 | DC2 | 1) Enter Character value in Customer ID Field | An error message" Customer ID must be numeric" must be shown | No error message is shown | Medium | Medium
53 | Closed | Nick Price | v2 | DC4 | 1) Customer ID cannot have Blank space 2) Press Tab | An error message "Customer ID cannot have blank space" must be shown | No error message is shown | Medium | Medium
54 | Closed | Nick Price | v2 | DC5 | 1) Enter first character space 2) Press Tab | An error message "Customer ID cannot have first character space" must be shown | No error message is shown | Medium | Medium
55 | Closed | Nick Price | v2 | CS4 | 1) Account no cannot have Blank space 2) Press Tab | An error message "Account no cannot have blank space" must be shown | An error message "Characters are not allowed" must be shown | Medium | Medium
56 | Closed | Nick Price | v2 | CS6 | 1) Do not enter a value in Amount Field 2) Press TAB and move to next Field | An error message "Amount Lower Limit cannot be empty" must be shown | No error message is shown | Medium | Medium
57 | Closed | Nick Price | v2 | CS7 | 1) Enter numeric value in Amount Lower Limit number Field | An error message "Amount Lower Limit must be numeric" must be shown | No error message is shown | Medium | Medium
58 | Closed | Nick Price | v2 | CS8 | 1) Enter Special Character In Amount Field | An error message "Amount Lower Limit cannot have special character" must be shown | No error message is shown | Medium | Medium
59 | Closed | Nick Price | v2 | CS9 | 1) Amount no cannot have Blank space 2) Press Tab | An error message "Amount Lower Limit cannot have blank space" must be shown | No error message is shown | Medium | Medium
60 | Closed | Nick Price | v2 | CS10 | 1) Enter first character space 2) Press Tab | An error message "Amount Lower Limit cannot have first character space" must be shown | No error message is shown | Medium | Medium
61 | Closed | Nick Price | v2 | CS11 | 1) Do not enter a value in Number of Transaction Field 2) Press TAB and move to next Field | An error message "Number of Transaction cannot be empty" must be shown | No error message is shown | Medium | Medium
62 | Closed | Nick Price | v2 | CS12 | 1) Enter character value in Number of Transaction number Field | An error message "Number of Transaction must be numeric" must be shown | No error message is shown | Medium | Medium
63 | Closed | Nick Price | v2 | CS13 | 1) Enter Special Character In Number for Transaction Field | An error message "Number of Transaction cannot have special character" must be shown | No error message is shown | Medium | Medium
64 | Closed | Nick Price | v2 | CS14 | 1) Number of transaction cannot have Blank space 2) Press Tab | An error message "Number of Transaction cannot have blank space" must be shown | No error message is shown | Medium | Medium
65 | Closed | Nick Price | v2 | CS15 | 1) Enter first character space 2) Press Tab | An error message "Number Of Transaction cannot have first character space" must be shown | No error message is shown | Medium | Medium
66 | Closed | Nick Price | v2 | IP1 | 1) Enter all required fields 2) Submit | Message Should be display "Customer added successfully !!" | Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/insrtCustomer.php on line 2 Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | High | High
67 | Closed | Nick Price | v2 | IP2 | 1) Enter all required field with existing user data 2) Submit | Message Should be displayed"Email address already exist" | Connection Error | High | High
68 | Closed | Nick Price | v2 | IP3 | 1) Enter all required fields 2) Submit | Message Should be displayed" customer records updated successfully!!" | Connection Error | High | High
69 | Closed | Nick Price | v2 | IP4 | 1) Enter all required fields 2) Submit | Message Should be display" customer records updated successfully!!" | Connection Error | High | High
70 | Closed | Nick Price | v2 | IP5 | 1) Enter the required fields 2) Submit | Message Should be display" You are not authorise to edit this customer!!" | Connection Error | High | High
71 | Closed | Nick Price | v2 | IP6 | 1) Enter all required fields 2) Submit | Message Should be display " account generated successfully" | Connection Error | High | High
72 | Closed | Nick Price | v2 | IP7 | 1) Enter all fields with customer id and account type already exist | Message Should be display " account generated successfully" | Connection Error | High | High
73 | Closed | Nick Price | v2 | IP8 | 1) Enter Account Number 2) Submit | Display Generated ministatement | Connection Error | High | High
74 | Closed | Nick Price | v2 | IP9 | 1) Enter account number 2) Submit | Message Should be display " account detail successfully updated" | Connection Error | High | High
75 | Closed | Nick Price | v2 | IP10 | 1) Enter all required fields 2) Submit | Display Generated ministatement | Connection Error | High | High
76 | Closed | Nick Price | v2 | IP11 | 1) Enter all required fields 2) Submit | Message Should be display"Account deleted Successfully" | Connection Error | High | High
77 | Closed | Nick Price | v2 | IP12 | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Connection Error | High | High
78 | Closed | Nick Price | v2 | IP13 | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Connection Error | High | High
79 | Closed | Nick Price | v2 | IP14 | 1)Enter all required field of deleted account 2)Submit | Message Should be display - "Account does not exist" | Connection Error | High | High
80 | Closed | Nick Price | v2 | IP15 | 1) Enter all required fields 2) Submit | Message Should be display"Customer could not be deleted " | Connection Error | High | High
81 | Closed | Nick Price | v2 | IP16 | 1)Enter all required field of deleted account 2)Submit | Message Should be display"You are not authorise to delete this account " | Connection Error | High | High
82 | Closed | Nick Price | v2 | IP17 | 1) Enter Account Number 2) Submit | Displayed Generated ministatement | Connection Error | High | High
83 | Closed | Nick Price | v2 | IP18 | 1) Enter all required fields 2) Submit | Display Generated Customized statement | Connection Error | High | High
84 | Closed | Nick Price | v2 | Exploratory Testing | Check the Name of the Website | Guru99 Bank | Gtpl Bank | High | Low